## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17435 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000238/2023-2024 | 1123/BMD | 24/05/2023 | 23/06/2023 | UNICON | 2.38 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17435 | Augmentation | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/00216/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 116/BQA | 10/01/2024 |  | Resource Division | 4 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17435 | Augmentation | Construction & commissioning of FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Mandalkuli, Zone-IIIB and its adjoining Mouzas under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2023-2024 | 1957/BQA | 18/07/2023 | 13/04/2024 | GOPAL CHANDRA CHOWDHURY | 147.48 | 127.2 | 86.25 | 100
5 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17435 | Augmentation | Route survey, preparation of DPR for Augmentation of Intake ,WTP & Rising main for Surface water based Piped water Supply Scheme for Mukutmanipur , Khatra & Ranibandh Under Jal Jeevan Mission of Khatra Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001212/2023-2024 | 486/BQA | 09/02/2024 | 10/03/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.42 | 0 | 0 | 0
Total | [13 empty] | 158.79 | 127.2 | 80.11