## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/00214/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000575/2023-2024 | 2030/BMD | 01/09/2023 | 30/12/2023 | TAPAN KUMAR DEY | 61.7 | 17.98 | 29.14 | 35
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries for Augmentation for Gargariya Zone A water supply scheme under Sarenga water supply scheme (BRGF Ph I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001036/2023-2024 | 2968/BMD | 29/02/2024 | 27/08/2024 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 37.8 | 18.77 | 49.65 | 40
4 | BANKURA |  | Bankura Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000833/2023-2024 | 2959/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.95 | 2.91 | 98.68 | 98
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Acceptance cum Formal work order for the work of Construction of Guard Piller for cable laying of river bed T/W with allied works for Gargaria Zone-A and Adjoining mouza for Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000320/2024-2025 | 861/BMD | 29/08/2024 | 27/12/2024 | PRADIP KUMAR DHABAL | 11.13 | 11.12 | 99.92 | 100
6 | BANKURA |  | Bankura Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.77 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | New Service Connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00382/2024-2025 | BP-2024-25-86 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | New 3 Phase Service Connection for Gargaria Zone B |  |  | BILL/00700/2024-2025 | 1BP-2024-25-167 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | New connection for 3 Gargaria Zone-B, Bikrampur Hatibari , JL-216 Plot-139 |  |  | BILL/01152/2024-2025 | BP-2024-25-270 | 19/11/2024 | 19/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.31 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Sinking of 2 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 2 Nos.Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000337/2023-2024 | 1961/BQA | 18/07/2023 | 02/07/2025 | PRINCE INDUTRIES (INDIA) | 221.68 | 66.56 | 30.03 | 82
11 | BANKURA |  | Bankura Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Work order for Laying of HDPE pipeline, Construction of Valve Chamber, Construction of Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 1829/BQA | 12/07/2024 | 02/01/2026 | SWAPAN KUMAR CHANDRA | 62.38 | 0 | 0 | 83
12 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries & MCC panel with other electromechanical accessories for Augmentation for Gargariya Zone-B and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/001095/2023-2024 | 3070/BMD | 12/03/2024 | 05/07/2025 | DEBJYOTI BASU | 67.22 | 28.47 | 42.36 | 55
13 | BANKURA |  | Bankura Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17438 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR, Repairing and painting of Over Head Reservoir (Capacity 500 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Gargaria, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2025-2026 | 1010/BQA | 25/04/2025 | 01/12/2025 | GOUTAM GHOSH | 31.47 | 0 | 0 | 0
Total | [13 empty] | 511.25 | 145.81 | 28.52