## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000613/2022-2023 | 569/BQA | 17/03/2023 | 16/04/2023 | M/S D.PALIT & CO. | 66.3 | 41.31 | 62.31 | 100
2 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/00212/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-A and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000563/2023-2024 | 2024/BMD | 01/09/2023 | 30/12/2023 | ABHIJIT MUKHERJEE | 70.19 | 48.69 | 69.37 | 65
4 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro allied electro-mechanical accessories for Augmentation for Dubrajpur Zone-A piped water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Simlapal , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/001091/2023-2024 | 3066/BMD | 12/03/2024 | 10/07/2024 | ABHIJIT MUKHERJEE | 26.71 | 22.72 | 85.04 | 35
5 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000828/2023-2024 | 2954/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 3.9 | 3.86 | 98.88 | 95
6 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 5.24 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/01659/2023-2024 | BP-2023-24-178 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.83 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of FHTC (Functional House Hold Tap Connection) and Construction of 3 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000308/2023-2024 | 1921/BQA | 13/07/2023 | 02/07/2025 | PRINCE INDUTRIES (INDIA) | 279.75 | 83.43 | 29.82 | 82
9 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Submersible Pump Motor set other allied work at Dubrajpur Zone-A & Dubrajpur Zone-B water supply scheme under Simlapal Block under BMD PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000199/2025-2026 | 645/BMD | 11/07/2025 | 09/10/2025 | M/S NABIN GOPAL SENGUPTA | 27.64 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 800 Cum., staging height 20 Mtr.), Pump House, Operator Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Dubrajpur, Zone-A water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001972/2024-2025 | 668/BQA | 12/03/2025 | 12/12/2025 | TAPAN KUMAR MANDAL | 24.01 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Laying of HDPE pipeline, Construction of Valve Chamber, Construction Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000248/2025-2026 | 1456/BQA | 02/07/2025 | 30/09/2025 | PRINCE INDUSTRIES (INDIA) | 147.3 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17440 | Augmentation | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for supervision and monitoring of Jal Jeevan Mission work under Khatra Sub-Division of Bankura Division, P.H.E. Dte. for the period from 01/07/2025 to 30/09/2025. | Assistant Engineer | Junior Engineer | ORD/000339/2025-2026 | 328\KSD | 24/06/2025 | 10/09/2025 | SEKH MUJTABA ALI | 0.37 | 0 | 0 | 0
Total | [13 empty] | 661.73 | 200.01 | 30.22