## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | SM/17441 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.32 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | SM/17441 | Augmentation | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). |  |  | BILL/00191/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | SM/17441 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machinery and other electro mechanical accessories for Augmentation of piped water supply scheme for Kenjakura and its adjoining Mouzas water supply scheme under Bankura Mechanical Division PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001090/2023-2024 | 3065/BMD | 12/03/2024 | 10/07/2024 | SWAPAN ENTERPRISE | 18.27 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | SM/17441 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000265/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.32 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | SM/17441 | Augmentation | Balance allied works of Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (phase-I) under Bankura Sadar Sub-Division of BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000167/2024-2025 | 1808/BQA | 11/07/2024 | 01/03/2026 | M/S TARUN KUMAR PATRA | 123.21 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | SM/17441 | Augmentation | Construction of High lift Pump House, Low lift Pump House cum chlorine room and Sinking of 01 no. 200 mm dia. Horizontal River Bed Tube Well under Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | Assistant Engineer | Junior Engineer | ORD/001392/2024-2025 | 39/BQA | 02/01/2025 | 01/04/2026 | PRANABANANDA TEWARY | 41.73 | 0 | 0 | 30
Total | [13 empty] | 187.34 | 0 | 0