## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Onda | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Jhatibone (JL No- 270) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | ORD/001088/2021-2022 | 282\BSD | 21/03/2022 | 05/04/2022 | INDRANIL DUTTA & ASSOCIATES | 3.46 | 3.46 | 100 | 98
2 | BANKURA | Onda | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS PROPOSED GROUND WATER BASED JHATIBONI PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- ONDA, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 1916/BQA | 13/07/2023 | 28/09/2026 | APEX ENTERPRISE | 221.76 | 77.7 | 35.04 | 75
3 | BANKURA | Onda | Bankura Mechanical | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Jhatiboni piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda Dist: Bankura. | Assistant Engineer | Estimator,Junior Engineer | ORD/000443/2023-2024 | 1772/BMD | 01/08/2023 | 14/09/2026 | INDRAJIT MITRA | 36.9 | 18.79 | 50.92 | 91
4 | BANKURA | Onda | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Soil Investigation work for construction of OHR (150 CUM CAPACITY) under Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000896/2023-2024 | 3047/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.57 | 0 | 0 | 100
5 | BANKURA | Onda | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 1.42 | 0 | 0 | 0
6 | BANKURA | Onda | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.91 | 0 | 0 | 0
7 | BANKURA | Onda | Bankura Mechanical | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Jhatiboni piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000124/2024-2025 | 1072/BMSD | 05/07/2024 | 03/09/2024 | M/S DE ENGINEERING CONCERN | 4.37 | 0 | 0 | 0
8 | BANKURA | Onda | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Material Requisition To Resource Division |  |  | RTOR000263/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.91 | 0 | 0 | 0
9 | BANKURA | Onda | Bankura Mechanical | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Submission of quotation for shifting of 11KV HTOH at Jhatiboni ws scheme under BMD ,PHED. |  |  | BILL/00287/2024-2025 | 1 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0 | 0
10 | BANKURA | Onda | Bankura Mechanical | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | SM/17577 | New | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. |  |  | BILL/01607/2023-2024 | BP-2023-24-134 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.73 | 0 | 0 | 0
Total | [13 empty] | 277.83 | 99.96 | 35.98