## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 1.42 | 0 | 0 | 0
2 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.09 | 0 | 0 | 0
3 | BANKURA | Onda | Bankura Mechanical | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. |  |  | BILL/00134/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.5 | 0 | 0 | 0
4 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
5 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000897/2023-2024 | 3048/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.58 | 0.58 | 100 | 100
6 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Kantabari (JL No- 265) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | ORD/001089/2021-2022 | 283\BSD | 21/03/2022 | 05/04/2022 | INDRANIL DUTTA & ASSOCIATES | 3.63 | 3.63 | 100 | 95
7 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Material Requisition To Resource Division |  |  | RTOR000260/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.09 | 0 | 0 | 0
8 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KANTABARI PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- ONDA, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 2345/BQA | 14/08/2023 | 01/01/2026 | GOUTAM BHATTACHRYYA | 260.01 | 83.69 | 32.19 | 49
9 | BANKURA | Onda | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Construction of Guard Room and Boundary Wall at Kantabari OHR Site under Proposed Ground Water based Kantabari Pipe Water Supply Scheme under Bankura Division, Block:- Onda. | Assistant Engineer | Junior Engineer | ORD/001403/2024-2025 | 46/BQA | 02/01/2025 | 02/08/2025 | RAHIBUDDIN MANDAL | 22.09 | 0 | 0 | 5
10 | BANKURA | Onda | Bankura Mechanical | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | SM/17578 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories at CWR site at mouza Punisole for Augmentation of Aguriband Punisole (Zone E) and Adj. mouzas piped water supply scheme in the Block Onda under Bankura Mechanical Division PHE Dte Block Bankura-I Dist Bankura | Assistant Engineer | Estimator | ORD/001009/2024-2025 | 2042/BMD | 07/03/2025 | 05/07/2025 | M.S. ENTERPRISE | 67.43 | 0 | 0 | 0
Total | [13 empty] | 367.02 | 87.9 | 23.95