## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Somsar (BRGF) Water Supply Scheme | SM/17579 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and installation of HSC Pumping machinery set with other allied works at CWR site for augmentation of Somsar water supply scheme under Bankura Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000341/2024-2025 | 785/BMD | 20/08/2024 | 17/04/2025 | ABHIJIT MUKHERJEE | 34.91 | 7.48 | 21.43 | 60
2 | BANKURA |  | Bankura Division | Augmentation of Somsar (BRGF) Water Supply Scheme | SM/17579 | Augmentation | Repairing and Renovation of RCC Elevated Over Head Reservoir of 250 cum capacity with staging height 20 m and other allied works in connection with Somsar (BRGF) water supply scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000373/2024-2025 | 2351/BQA | 09/09/2024 | 01/04/2025 | TAPAN KUMAR MANDAL | 9.49 | 0 | 0 | 100
3 | BANKURA |  | Bankura Division | Augmentation of Somsar (BRGF) Water Supply Scheme | SM/17579 | Augmentation | Sinking of 1 no. 300mm X 200mm X 240m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Laying of distribution system and Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Somsar W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :-Kumna, No. of Mouzas Covered :- 3 nos., Name of Mouzas & JL No.:-Bhagabatipur (1), Palashdanga (3), Kumna (4) Total No. House Hold:- 320 | Assistant Engineer | Junior Engineer | ORD/000797/2022-2023 | 680/BQA | 28/03/2023 | 01/04/2025 | SUBHENDU SEKHAR GORAI | 53.76 | 38.81 | 72.19 | 75
Total | [13 empty] | 98.16 | 46.29 | 47.16