## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Augmentation of Kushmuri Zone-B Water Supply Scheme |  |  | BILL/00177/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Construction of 2nos. boundary wall approx 60 mtr long for Kushmuri Zone- B water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2023-2024 | 3017/BQA | 03/11/2023 | 01/07/2025 | FARUK ALI KHAN | 8.43 | 0 | 0 | 15
3 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- B W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Jinkara (19), Paharpur (55), Bara Gobindapur (59), Kapcit (23), Fatepur (56) Total No. House Hold:- 190 | Assistant Engineer | Junior Engineer | ORD/000686/2023-2024 | 2632/BQA | 21/09/2023 | 01/01/2026 | TAPAS KUMAR HAZRA | 56.51 | 0 | 0 | 75
4 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Construction of 2 nos. Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for Kushmuri Zone- B Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 2633/BQA | 21/09/2023 | 02/10/2025 | SK FAZLUL ALAM | 13.22 | 0 | 0 | 95
5 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Sinking of 3 nos. 300mm X 200mm X 240m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Kushmuri Zone- B piped water supply scheme within Indas Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001150/2023-2024 | 360/BQA | 06/02/2024 | 22/03/2024 | SUBHADIP KOLE | 51.08 | 0 | 0 | 5
6 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Laying distribution system for Kushmuri Zone- B W/S Scheme (BRGF Phase-I) within Indas Block in connection with Jal Jeevan Mission (JJM) under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2023-2024 | 2631/BQA | 21/09/2023 | 01/08/2025 | GON ASSOCIATES | 15.03 | 0 | 0 | 97
Total | [13 empty] | 145.78 | 0 | 0