## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Augmentation of Kushmuri Zone-B Water Supply Scheme |  |  | BILL/00177/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Construction of 2nos. boundary wall approx 60 mtr long for Kushmuri Zone- B water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2023-2024 | 3017/BQA | 03/11/2023 | 01/07/2025 | FARUK ALI KHAN | 8.43 | 2.72 | 32.23 | 15
3 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000610/2023-2024 | 2084/BMD | 12/09/2023 | 26/10/2026 | GOENKA ENTERPRISE | 70.65 | 33.7 | 47.7 | 60
4 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- B W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Jinkara (19), Paharpur (55), Bara Gobindapur (59), Kapcit (23), Fatepur (56) Total No. House Hold:- 190 | Assistant Engineer | Junior Engineer | ORD/000686/2023-2024 | 2632/BQA | 21/09/2023 | 01/10/2025 | TAPAS KUMAR HAZRA | 56.51 | 33.35 | 59.02 | 75
5 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Construction of 2 nos. Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for Kushmuri Zone- B Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 2633/BQA | 21/09/2023 | 02/10/2025 | SK FAZLUL ALAM | 13.22 | 5.06 | 38.3 | 95
6 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | SM/17682 | Augmentation | Sinking of 3 nos. 300mm X 200mm X 240m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Kushmuri Zone- B piped water supply scheme within Indas Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001150/2023-2024 | 360/BQA | 06/02/2024 | 22/03/2024 | SUBHADIP KOLE | 51.08 | 20.78 | 40.68 | 5
Total | [13 empty] | 201.4 | 95.61 | 47.47