## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-B Water Supply Scheme | SM/17683 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rol (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000378/2023-2024 | 1704/BMD | 28/07/2023 | 26/09/2023 | R.N.S. TRADING | 73.25 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-B Water Supply Scheme | SM/17683 | Augmentation | Augmentation of Rol Zone-B Water Supply Scheme |  |  | BILL/00183/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-B Water Supply Scheme | SM/17683 | Augmentation | Load enhancement charges for ROLL ZONE B water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00431/2024-2025 | BP-2024-25-107 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Rol Zone-B Water Supply Scheme | SM/17683 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF ROL ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000333/2023-2024 | 2003/BQA | 19/07/2023 | 28/03/2026 | PRINCE INDUTRIES (INDIA) | 183.13 | 90.98 | 49.68 | 80
5 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-B Water Supply Scheme | SM/17683 | Augmentation | New 3 phase connection at Dhamur (Roll Zone-B) |  |  | BILL/01330/2024-2025 | BP-2024-25-331 | 29/01/2025 | 29/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-B Water Supply Scheme | SM/17683 | Augmentation | New three service phase connection for boosting TW site of Arapur(Gopalpur) under Roll Zone -B water supply scheme under Bankura Mechanical Division P.H.E Dte. |  |  | BILL/01344/2024-2025 | BP-2024-25-332 | 29/01/2025 | 29/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.26 | 0 | 0 | 0
Total | [13 empty] | 266.43 | 90.98 | 34.15