## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | Augmentation of Indas Water Supply Scheme |  |  | BILL/00188/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | Sinking of1 no. 300mm X 200mm X 250m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for INDAS piped water supply scheme within Indas Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000670/2023-2024 | 2624/BQA | 21/09/2023 | 16/08/2024 | D. S. ENTERPRISE | 18.93 | 0 | 0 | 70
3 | BANKURA |  | Bankura Division | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | Sinking of Tubewell and Construction of Boundary Wall & Pump House for Augmentation of Indas Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001355/2024-2025 | 3172/BQA | 24/12/2024 | 24/03/2025 | BEAUTY CHATTERJEE | 26.99 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for INDAS Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000675/2023-2024 | 2626/BQA | 21/09/2023 | 16/02/2025 | ARIJIT GUHA | 6.6 | 0 | 0 | 92
5 | BANKURA |  | Bankura Division | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | Construction of boundary wall approx 60 mtr long for INDAS water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000867/2023-2024 | 3016/BQA | 03/11/2023 | 02/01/2024 | GOLAM KHAJA KHAN | 4.44 | 0 | 0 | 90
6 | BANKURA |  | Bankura Mechanical | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | New Service Connection for INDUS BPHC CAMPUS (JL NO-14, PLOT-1947)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00013/2024-2025 |  | 19/04/2024 | 19/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | New Service Connection for INDUS BPHC CAMPUS (JL NO-14, PLOT-1947)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00012/2024-2025 | BP-2024-25-8 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation of Indas Water Supply Scheme | SM/17684 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for Augmentation of Indas water supply scheme under indus Block under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000117/2024-2025 | 428/BMD | 27/06/2024 | 23/04/2025 | M/S BIPUL BANERJEE | 35.24 | 0 | 0 | 40
Total | [13 empty] | 101.32 | 0 | 0