## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at OHR, CWR and Tail end site for Augmentation of Radhanagar (Zone I) piped water supply scheme(BRGF Phase I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000120/2024-2025 | 430/BMD | 27/06/2024 | 25/10/2024 | M/S NABIN GOPAL SENGUPTA | 61.72 | 17.33 | 28.07 | 100
2 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Submission of quotation for new service connection at Swasan of Radhanagar Zone-I ws scheme under BMD ,PHED. |  |  | BILL/00295/2024-2025 | 1 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.85 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Submission of Quotation for Kankila OHR of Radhanagar w/s scheme. |  |  | BILL/00536/2024-2025 | 1 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Submission of quotation for new service connection at Sarada Pally (Bankati) of Radhanagar Zone-I ws scheme under BMD ,PHED. |  |  | BILL/00294/2024-2025 | 1 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RADHANAGAR ZONE-I PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000379/2023-2024 | 2040/BQA | 24/07/2023 | 31/12/2025 | SIB SANKAR CHOWDHURY | 221.76 | 94.79 | 42.74 | 90
6 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Radhanagar (Zone-I) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000373/2023-2024 | 1701/BMD | 28/07/2023 | 01/07/2025 | TAPAN KUMAR SARKAR | 40.91 | 22.96 | 56.12 | 82
7 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineryes with allied works for Augmentation of Radhanagar Zone-I Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 863/BMD | 29/08/2024 | 22/12/2025 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 20.86 | 0 | 0 | 50
8 | BANKURA |  | Bankura Division | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Radhanagar Zone - I Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/000361/2025-2026 | 1802/BQA | 19/08/2025 | 17/11/2025 | JAMIRUL CONSTRUCTION | 12.72 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Radhanagar Zone-I Water Supply Scheme | SM/17690 | Augmentation | Instalation of scheme information board for 1 no. sites of Augmentation of Radhanagar Zone-I Water Supply Scheme (SM/17690) & 2 nos. sites of Augmentation of Radhanagar Zone-II Water Supply Scheme (SM/17691) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001810/2024-2025 | 536/VSD | 27/09/2024 | 12/10/2024 | SANTANU GARAI | 0.45 | 0 | 0 | 0
Total | [13 empty] | 372.26 | 135.07 | 36.29