## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | Augmentation of Radhanagar Zone-II Water Supply Scheme |  |  | BILL/00163/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | Submission of Quotation for new service connection at Mouza Janta of Augmentation of Radhanagar ws scheme under BMD ,PHE Dte. |  |  | BILL/00297/2024-2025 | 1 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.68 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | Submission of quotation for new service connection at mouza Layer of Radhanagar ws scheme under BMD,PHED |  |  | BILL/00298/2024-2025 | 1 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.42 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | Submission of quotation for Radhanagar OHR of Radhanagar w/s scheme. |  |  | BILL/00535/2024-2025 | BP-2024-25-142 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Radhanagar (Zone-II) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000376/2023-2024 | 1702/BMD | 28/07/2023 | 18/04/2025 | GOENKA ENTERPRISE | 40.9 | 15.11 | 36.95 | 45
6 | BANKURA |  | Bankura Division | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF RADHANAGAR ZONE-II PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000399/2023-2024 | 2084/BQA | 27/07/2023 | 02/04/2026 | S B ASSOCIATES | 124.07 | 61.3 | 49.41 | 95
7 | BANKURA |  | Bankura Mechanical | Augmentation of Radhanagar Zone-II Water Supply Scheme | SM/17691 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at OHR for Augmentation of Radhanagar (Zone II) piped water supply scheme(BRGF Phase I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000121/2024-2025 | 431/BMD | 27/06/2024 | 22/06/2025 | PRADIP KUMAR DHABAL | 19.46 | 0 | 0 | 61
Total | [13 empty] | 202.68 | 76.41 | 37.7