## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000516/2023-2024 | 1881/BMD | 17/08/2023 | 01/07/2025 | EASTERN INDIA SALES & SERVICE | 48.95 | 0 | 0 | 45
2 | BANKURA |  | Bankura Division | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BETANAL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000501/2023-2024 | 2351/BQA | 14/08/2023 | 10/05/2024 | SUBHANKAR BANERJEE | 168.53 | 0 | 0 | 18
3 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Augmentation of Betanal Zone-A Water Supply Scheme |  |  | BILL/01624/2023-2024 | BP-2023-24-151 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.77 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and Installation of Valves with other electro-mechanical accessories at Betanal CWR pipe line based water supply schemes of Indus under B.M.D, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2024-2025 | 777/BMD | 20/08/2024 | 02/08/2025 | M/S SWAPAN BANERJEE | 12.56 | 0 | 0 | 95
5 | BANKURA |  | Bankura Division | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Construction of Pump House for Augmentation of Betanal (Zone - A) Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001350/2024-2025 | 3167/BQA | 24/12/2024 | 24/03/2025 | M/S ASHA ENGINEERING | 6.52 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-A Water Supply Scheme | SM/17692 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical accessories at boosting P.H for augmentation of Betanal Zone A water supply scheme under B.M.D. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2025-2026 | 151/BMD | 30/04/2025 | 29/07/2025 | ABHIJIT MUKHERJEE | 18.95 | 0 | 0 | 0
Total | [13 empty] | 258.29 | 0 | 0