## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-A Water Supply Scheme | SM/17693 | Augmentation | Augmentation of Rol Zone-A Water Supply Scheme |  |  | BILL/00182/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-A Water Supply Scheme | SM/17693 | Augmentation | Load enhancement charges for ROLL ZONE A water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00433/2024-2025 | BP-2024-25-106 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Rol Zone-A Water Supply Scheme | SM/17693 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rol (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000377/2023-2024 | 1703/BMD | 28/07/2023 | 30/03/2025 | M/S BIPUL BANERJEE | 39.07 | 19.6 | 50.17 | 50
4 | BANKURA |  | Bankura Division | Augmentation of Rol Zone-A Water Supply Scheme | SM/17693 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF ROL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000402/2023-2024 | 2087/BQA | 27/07/2023 | 01/04/2025 | S.N POLYMERS PVT LTD | 107.14 | 61.59 | 57.49 | 50
Total | [13 empty] | 147.75 | 81.19 | 54.95