## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.33 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000504/2023-2024 | 2354/BQA | 14/08/2023 | 05/01/2031 | SUBHANKAR BANERJEE | 336.21 | 33.52 | 9.97 | 14
3 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Soil Investigation work for construction of OHR (450 CUM CAPACITY) under Augmentation of Kheyarkanali OHR (Zone- J) under Bankura- I, II & Barjora W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2023-2024 | 3035/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.49 | 0.47 | 96.86 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000258/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.33 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | New service connection for KHYERKANAKI (Zone-J) OHR site under Bankura-I,II & Barjora water supply scheme(BRGF Ph-I project) |  |  | BILL/01145/2024-2025 | BP-2024-25-280 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.31 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Laying Rising Main, Construction of Boundary wall, Staff Room & Toilet of Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001412/2024-2025 | 51/BQA | 02/01/2025 | 02/04/2025 | BEAUTY CHATTERJEE | 33.88 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electro mechanical accessories at OHR site of Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 854/BMD | 29/08/2024 | 22/11/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 40.9 | 0 | 0 | 89
8 | BANKURA |  | Bankura Mechanical | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Acceptance cum Formal work order for the work of Replacement of Valves on the delivery line at IBS Belboni, for Augmentation work for Khyerkanali ( Zone-J) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 440./BMD | 27/06/2024 | 23/04/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 42.76 | 23.6 | 55.18 | 55
9 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Khyerkanali (Zone- J) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001192/2023-2024 | 445/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 2 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 242/1 -2) in between Beliatore Rly. Station and Belboni Rly. station in Belboni mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under KHYERKANALI(Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001337/2024-2025 | 3161/BQA | 24/12/2024 | 23/01/2025 | SIBSANKAR CHOWDHURY | 51.9 | 51.84 | 99.88 | 100
11 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Crossing of Road by Jack pushing method ( 600 mm dia Hump pipe (NP3/NP4 & MS Pipe for casing) & 200mm dia carrier pipe for Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Location of Site:- Near Belboni IBS Air valve point. | Assistant Engineer | Junior Engineer | ORD/001343/2024-2025 | 3182/BQA | 24/12/2024 | 24/03/2025 | I R CONSTRUCTION | 11.42 | 6.9 | 60.45 | 100
12 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 246/3 -4) in between Belboni Rly. Station - Baliator Rly. station, Block Barjora ,by HDD method with 300 mm (OD) MS Casing Pipe with 100 mm dia. MS carrier pipe for Proposed Surface Water Based Dhabani PIped Water Supply Scheme & Augmentation works for KHYERKANALI (Zone- J) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001935/2024-2025 | 658/BQA | 11/03/2025 | 10/04/2025 | M/S TARUN KUMAR PATRA | 44.95 | 0 | 0 | 2
Total | [13 empty] | 569.48 | 116.33 | 20.43