## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.33 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000504/2023-2024 | 2354/BQA | 14/08/2023 | 05/01/2031 | SUBHANKAR BANERJEE | 336.21 | 0 | 0 | 14
3 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Soil Investigation work for construction of OHR (450 CUM CAPACITY) under Augmentation of Kheyarkanali OHR (Zone- J) under Bankura- I, II & Barjora W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2023-2024 | 3035/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.49 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000258/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.33 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | New service connection for KHYERKANAKI (Zone-J) OHR site under Bankura-I,II & Barjora water supply scheme(BRGF Ph-I project) |  |  | BILL/01145/2024-2025 | BP-2024-25-280 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.31 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Laying Rising Main, Construction of Boundary wall, Staff Room & Toilet of Augmentation of KHEYARKANALI OHR (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001412/2024-2025 | 51/BQA | 02/01/2025 | 02/04/2025 | BEAUTY CHATTERJEE | 33.88 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electro mechanical accessories at OHR site of Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 854/BMD | 29/08/2024 | 22/11/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 40.9 | 0 | 0 | 89
8 | BANKURA |  | Bankura Mechanical | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17695 | Augmentation | Acceptance cum Formal work order for the work of Replacement of Valves on the delivery line at IBS Belboni, for Augmentation work for Khyerkanali ( Zone-J) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 440./BMD | 27/06/2024 | 23/04/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 42.76 | 0 | 0 | 55
Total | [13 empty] | 459.21 | 0 | 0