## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Augmentation of Chuamasina Zone-A Water Supply Scheme |  |  | BILL/00166/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Exsistingt TW I,III,IV and V for Augmentation of Chuamosina and Adjoining mouza water supply scheme (Zone-A) Block-Bishnupurunder Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 486/BMD | 09/07/2024 | 06/11/2024 | INDRAJIT MITRA | 31.42 | 20.67 | 65.78 | 40
3 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Submission of quotation for new service connection at Chuamosina Zone-A Mouza Arjunpur. SM/17696. |  |  | BILL/00724/2024-2025 | BP-2024-25-196 | 23/08/2024 | 23/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.35 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Quotation as per WBSEDCL Procedure -A (2010) on turn key /full deposit basis for new service connection at Mouza Jhatabon under Bankura Mechanica Division ,PHE Dte. |  |  | BILL/00730/2024-2025 | BP-2024-25-207 | 03/09/2024 | 03/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.74 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Submission of quotation for new service connection at Chuamosina Zone -A Mouza Chuamosina JL no 17. SM /17696. |  |  | BILL/00725/2024-2025 | BP-2024-25-197 | 28/08/2024 | 28/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.6 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHUAMASINA ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000393/2023-2024 | 2053/BQA | 24/07/2023 | 19/04/2024 | SIB SANKAR CHOWDHURY | 230.45 | 60.77 | 26.37 | 15
7 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chuamasina (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000523/2023-2024 | 1887/BMD | 17/08/2023 | 02/06/2026 | SUNRISE ENGINEERING CORPORATION | 75.13 | 0 | 0 | 75
8 | BANKURA |  | Bankura Division | Augmentation of Chuamasina Zone-A Water Supply Scheme | SM/17696 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Chuamosina (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001354/2024-2025 | 3171/BQA | 24/12/2024 | 24/03/2025 | MUKHERJEE CONSTRUCTION | 12.97 | 0 | 0 | 5
Total | [13 empty] | 368.16 | 81.44 | 22.12