## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Cherabasta (Zone-K) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000312/2023-2024 | 1411/BMD | 18/07/2023 | 16/09/2023 | DEBJYOTI BASU | 81.81 | 65.59 | 80.18 | 80
2 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Augmentation works for CHERABASTA (ZONE - K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Phase - I Project). | Assistant Engineer | Junior Engineer | ORD/000331/2023-2024 | 2001/BQA | 19/07/2023 | 28/03/2026 | S.N POLYMERS PVT LTD | 297.16 | 136.23 | 45.85 | 55
3 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of CHERABASTA (Zone - K)) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Cherabasta No.of Mouza :- 01 nos. Teleghara . Total House Hold -13 nos. | Assistant Engineer | Junior Engineer | ORD/000562/2022-2023 | 61/BSD | 24/01/2023 | 31/01/2023 | COSMIC CONSTRUCTION | 0.97 | 0.97 | 99.74 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at Gopinathpur (271), Teleghara (286 ), Bagneja (287), Ailtha (281) & Cherabasta (256), of Swajal Gram/Har Ghar Jal Villages for awareness generation among the pepole of Bankura Sadar Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001060/2023-2024 | 1176/BSD | 22/11/2023 | 07/12/2023 | TAPAS DEY | 0.69 | 0.68 | 97.77 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.92 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00136/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- I at Tail End site of Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II and Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000315/2024-2025 | 856/BMD | 29/08/2024 | 27/12/2024 | CHAKRABORTY MINING & ENGINEERING. | 9.23 | 3.87 | 41.97 | 60
8 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Cherabasta (Zone- K) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001193/2023-2024 | 446/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 2.31 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000257/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.92 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Wayleave/Track crossing proposal with application ID:SER-ADRA-WL-12 For Cherabasta (zone-k) SM Code-SM/SM/17697 |  |  | BILL/00060/2024-2025 | FHTC/04 | 26/04/2024 | 26/04/2024 | SOUTH EASTERN RAILWAY | 0.11 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Payment of Wayleave facility charges of CHERABASTA (ZONE-K) W/S Scheme. Scheme Code-SM/17697. Application ID-SER-ADRA-2024-WL-12 |  |  | BILL/00275/2024-2025 | BP-113/2024-25 | 19/06/2024 | 19/06/2024 | SOUTH EASTERN RAILWAY | 6.4 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Construction of High lift Pump House, Pump House cum chlorine room & Toilet, Boundary wall of Augmentation of CHERABASTA (Zone - K) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001668/2024-2025 | 360/BQA | 07/02/2025 | 01/01/2026 | SAIKAT CHOWDHURY | 37.52 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17697 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 234/10 -11) in between Bikna Rly. Station and Bankura Rly. station in Mobarakpur mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for Rising main pipe line under Augmentation of CHERABASTA (Zone - K) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000192/2025-2026 | 1327/BQA | 17/06/2025 | 01/08/2025 | GOPAL CHANDRA CHOWDHURY | 47.66 | 0 | 0 | 0
Total | [13 empty] | 489.2 | 207.34 | 42.38