## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.95 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00137/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Acceptance cum Formal work order for the work ofProviding and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Chaterkanali (Zone-L) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 1464/BMD | 18/07/2023 | 16/09/2023 | TAPAN KUMAR DEY | 81.77 | 52.56 | 64.28 | 64
4 | BANKURA |  | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000255/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.95 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Laying of 150 mm dia underground water pipe line carrier with 600 mm dia MS casing under Railway Track of KM 239/4-5 in beet ween Rly station Bikna Nabanda station beet ween Bankura Masagram section |  |  | BILL/00026/2024-2025 | FHTC/04 | 18/04/2024 | 18/04/2024 | SOUTH EASTERN RAILWAY | 5.63 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Construction of High lift Pump House at OHR Site of departmental design & drawing in connection with Jal Jeevan Mission (JJM) for Augmentation of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2024-2025 | 2343/BQA | 09/09/2024 | 01/07/2026 | ASHIS PAL | 18 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 239/4 -5) in between Bikna-Nobanda) Rly. Station and Bankura-Masagram Rly. station in Nabanda mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under Augmentation of CHAtarkanali (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000191/2025-2026 | 1326/BQA | 17/06/2025 | 01/08/2025 | M/S TARUN KUMAR PATRA | 50.82 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17698 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Chatarkanali (Zone- L) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001194/2023-2024 | 447/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 1.69 | 0 | 0 | 100
Total | [13 empty] | 163.31 | 52.56 | 32.18