## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Dhengasole Water Supply Scheme | SM/17699 | Augmentation | Augmentation of Dhengasole Water Supply Scheme |  |  | BILL/00171/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Dhengasole Water Supply Scheme | SM/17699 | Augmentation | Augmentation of Dhengasole Water Supply Scheme |  |  | BILL/01608/2023-2024 | BP-2023-24-135 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.74 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Dhengasole Water Supply Scheme | SM/17699 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF DHENGASOLE PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000386/2023-2024 | 2046/BQA | 24/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 166.93 | 0 | 0 | 90
4 | BANKURA |  | Bankura Mechanical | Augmentation of Dhengasole Water Supply Scheme | SM/17699 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW at OHR and PH site for Augmentation of Dhengasole and Adjoining mouza water supply scheme Block-Bishnupur under Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000153/2024-2025 | 496/BMD | 09/07/2024 | 04/07/2025 | PRADIP KUMAR DHABAL | 23.32 | 0 | 0 | 61
5 | BANKURA |  | Bankura Mechanical | Augmentation of Dhengasole Water Supply Scheme | SM/17699 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro-mechanical accessories at Boosting tubewell for Augmentation of Dhengasole piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 143/BMD | 30/04/2025 | 29/07/2025 | TAPAN KUMAR SARKAR | 21.51 | 0 | 0 | 0
Total | [13 empty] | 221.01 | 0 | 0