## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Supplying fitting fixing of different dia. CIDF Sluice Valve & fittings & Construction of valve chamber in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001037/2023-2024 | 3465/BQA | 19/12/2023 | 18/03/2024 | GOUTAM GOSWAMI | 3.84 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.11 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for proposed Tubewell-II of Bikrampur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001087/2023-2024 | 3063/BMD | 12/03/2024 | 08/09/2024 | M/S BIPUL BANERJEE | 25.39 | 11.78 | 46.4 | 40
4 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Onda, Name of OHR - Bikrampur, No.of Mouza :- 13, Name of mouza:- Patadubi, Angadpur, Bhaluka, Karra, Hemchabad, Bikrampur, Indkata, Lohari Brindaban, Kochkhalui, Brindabanpur, Shusina Gobindarampur, Ramar Gram & Hatiband , Total House Hold - 150 nos. | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 798/BQA | 11/04/2023 | 26/05/2023 | BEAUTY CHATTERJEE | 51.43 | 49.17 | 95.61 | 95
5 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000148/2023-2024 | 1348/BQA | 02/06/2023 | 17/07/2023 | BROTIN UPADHYAY | 14.23 | 9.57 | 67.26 | 100
6 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000253/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.11 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Replacement TW for Augmentation of Bikrampur and Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Estimator,Junior Engineer | ORD/000139/2024-2025 | 445/BMD | 27/06/2024 | 17/02/2026 | M/S SWAPAN BANERJEE | 19.55 | 0 | 0 | 80
8 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Extra HDPE Pipe Line for Hatibandh & Karrah in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000202/2024-2025 | 1890/BQA | 15/07/2024 | 13/09/2024 | SWAPAN KUMAR DE | 15.26 | 0 | 0 | 5
9 | BANKURA |  | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | SM/17700 | Augmentation | Sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of BIKRAMPUR and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001375/2024-2025 | 29/BQA | 02/01/2025 | 19/09/2025 | SANJOY MONDAL | 12.81 | 0 | 0 | 85
Total | [13 empty] | 144.72 | 70.52 | 48.73