## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) Block - Barjora, Name of OHR - BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone - IV), No. of Mouza :- 06 nos., Name of mouza:- (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), No. of Household-1690 nos | Assistant Engineer | Junior Engineer | ORD/000811/2022-2023 | 714/BQA | 30/03/2023 | 28/06/2023 | ASHIS PAL | 31.43 | 31.43 | 100 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.18 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). |  |  | BILL/00158/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Sinking of 03 (Three) no. 200 mm X 165 mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 715/BQA | 30/03/2023 | 14/05/2023 | GANESH ROY | 12.95 | 8.34 | 64.41 | 90
5 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IV) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 1402/BMD | 18/07/2023 | 16/09/2023 | WEST BENGAL ENGINEERING CO. | 81.8 | 54.19 | 66.24 | 55
6 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories at Tail End at GOPBANDHI, Saharjora for Augmentation works under BARJORA (ZONE -IV) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000183/2024-2025 | 578/BMD | 24/07/2024 | 21/11/2024 | NUPUR CHANDRA HALDER | 13.15 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000251/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.18 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Laying of HDPE Pipe line, Construction of Pump House cum chlorine room, Construction of Pump House & Toilet at head work site & Boundary wall under Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer |  | ORD/001394/2024-2025 | 41/BQA | 02/01/2025 | 02/04/2025 | PRAVAT SARKAR | 56.51 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Submersible pumping machineries and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I) ( Zone IV) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001037/2023-2024 | 2969/BMD | 29/02/2024 | 23/02/2026 | M/S S.G. ENTERPRISE | 27.54 | 0 | 0 | 99
10 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | Creation of Balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) Block - Barjora, Name of OHR - BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone - IV), No. of Mouza :- 06 nos., Name of mouza:- (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), No. of Household- 200 nos | Assistant Engineer | Junior Engineer | ORD/000814/2022-2023 | 716/BQA | 30/03/2023 | 28/06/2023 | MOHAN KUMAR ROY | 43.66 | 18.04 | 41.31 | 90
11 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | SM/17701 | Augmentation | 100 mm dia & 150 mm dia MS delivery main connecting line from 2 (two) nos Vertical Tube Well to CWR & CWR to OHR Inlet pipe ,1 (one) nos Vertical Tube Well to Distribution pipe in connection with Jal Jeevan Mission (JJM) for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 717/BQA | 30/03/2023 | 28/06/2023 | SANDHYA DEY | 4.95 | 0 | 0 | 22
Total | [13 empty] | 275.35 | 111.99 | 40.67