## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 12.64 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 3467/BQA | 20/12/2023 | 20/12/2023 | Resource Division | 11.89 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 4.39 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' |  |  | BILL/00128/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at Intermediate Boosting pumping station(IBS) and sub-station equipments at Upargora under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000338/2023-2024 | 1470/BMD | 18/07/2023 | 16/09/2023 | DAS ENTERPRISE | 173.06 | 0 | 0 | 70
6 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Construction of Boundary wall for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000696/2023-2024 | 2642/BQA | 21/09/2023 | 20/11/2023 | M/S SUPRIYA CHATTERJEE | 18.14 | 0 | 0 | 2
7 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Construction of 200 Cum. Clear Water Reservoir with allied works for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000695/2023-2024 | 2641/BQA | 21/09/2023 | 19/04/2024 | RUFIKUL MONDAL | 43.9 | 0 | 0 | 65
8 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Distribution of Pipeline and Creation of Balance FHTC (Functional House Hold Tap Connection) for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000864/2023-2024 | 3020/BQA | 03/11/2023 | 02/01/2024 | M/S BIPUL BANERJEE | 78.59 | 0 | 0 | 6
9 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Dhaban (Zone-A) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000845/2023-2024 | 2971/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.98 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000250/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 4.39 | 0 | 0 | 0
11 | BANKURA |  | Bankura Mechanical | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | New service connection for DHABAN water supply scheme under BMD PHE Dte. (SM code : SM/17702) |  |  | BILL/00429/2024-2025 | BP-2024-25-105 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0 | 0
12 | BANKURA |  | Bankura Mechanical | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Acceptance cum Formal work order for the work of Replacement of Valves on delivery line at Intermediate Boosting pumping station(IBS) at Upargora under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura for Augmentation work Dhaban( Zone-A) under Saltora-Chhatna Water supply scheme (BRGF Phase-I) | Assistant Engineer | Junior Engineer | ORD/000612/2023-2024 | 2086/BMD | 12/09/2023 | 15/05/2025 | DAS ENTERPRISE | 17.65 | 0 | 0 | 60
13 | BANKURA |  | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Construction of Pump House at CWR site for Augmentation of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000694/2023-2024 | 2640/BQA | 21/09/2023 | 01/01/2026 | SRIKANTA MONDAL | 18.91 | 0 | 0 | 0
14 | BANKURA |  | Bankura Mechanical | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17702 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machinery and other electromagnetically accessories for Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001089/2023-2024 | 3064/BMD | 12/03/2024 | 06/05/2025 | WEST BENGAL ENGINEERING CO. | 84.1 | 0 | 0 | 37
Total | [13 empty] | 478.15 | 0 | 0