## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17703 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.74 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17703 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.74 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17703 | Augmentation | " Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Hapania(Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000622/2023-2024 | 2541/BQA | 11/09/2023 | 02/01/2026 | GOUTAM BHATTACHRYYA | 48.28 | 19.85 | 41.12 | 50
4 | BANKURA |  | Bankura Division | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17703 | Augmentation | " Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Hapania(Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000619/2023-2024 | 2540/BQA | 11/09/2023 | 10/12/2023 | BISWARUP BOSE | 48.28 | 0 | 0 | 5
Total | [13 empty] | 104.03 | 19.85 | 19.08