## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17704 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.46 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17704 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Jamtora (Zone - I) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000739/2023-2024 | 2353/BQA | 14/08/2023 | 10/05/2024 | M/S BIPUL BANERJEE | 109.07 | 72.58 | 66.54 | 45
3 | BANKURA |  | Bankura Division | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17704 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Jamtora (Zone-G) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2023-2024 | 2972/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 2.37 | 1.93 | 81.4 | 100
4 | BANKURA |  | Bankura Division | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17704 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.46 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17704 | Augmentation | Laying of balance distribution system of Pipeline in connection with Jal Jeevan Mission (JJM) for Augmentation of Chinabari (Zone - H) (Part) and Augmentation of Jamtora (Zone - G) (Part) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000102/2025-2026 | 1231/BQA | 02/06/2025 | 31/08/2025 | ZAKIR HOSSIN MONDAL | 116.21 | 0 | 0 | 0
Total | [13 empty] | 230.58 | 74.51 | 32.31