## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17705 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.81 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17705 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works, Construction of Pump House and 100 Cum. CWR for Augmentation of Chinabari (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000405/2023-2024 | 2092/BQA | 27/07/2023 | 22/04/2024 | MADHU SUDAN RAKSHIT | 177.01 | 0 | 0 | 62
3 | BANKURA |  | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17705 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Chinabari (Zone-H) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000847/2023-2024 | 2973/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.09 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17705 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000245/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.81 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17705 | Augmentation | Construction of Pump House including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of Chinabari (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001667/2024-2025 | 358/BQA | 07/02/2025 | 05/08/2025 | SAYED PAHALOWAN | 22.42 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17705 | Augmentation | Laying of balance distribution system of Pipeline in connection with Jal Jeevan Mission (JJM) for Augmentation of Chinabari (Zone - H) (Part) and Augmentation of Jamtora (Zone - G) (Part) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000102/2025-2026 | 1231/BQA | 02/06/2025 | 31/08/2025 | ZAKIR HOSSIN MONDAL | 116.21 | 0 | 0 | 0
Total | [13 empty] | 323.36 | 0 | 0