## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17706 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of keshra (Zone - I) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000309/2023-2024 | 1955/BQA | 18/07/2023 | 01/10/2026 | AJIT KUMAR PAUL | 114.57 | 59.15 | 51.63 | 26
2 | BANKURA |  | Bankura Division | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.09 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000243/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.09 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17706 | Augmentation | Laying of distribution system of pipeline and other allied works with Jal Jeevan Mission (JJM) of augmentation work for keshra, (Zone- I) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR -keshra, No.of Mouza :- ( Khirpai, Hanulia, Lakshmishol, Pithabad, Bhandarber, Shaldiha) | Assistant Engineer | Junior Engineer | ORD/000153/2025-2026 | 1298/BQA | 17/06/2025 | 01/04/2026 | BEAUTY CHATTERJEE | 43.78 | 0 | 0 | 1
Total | [13 empty] | 162.53 | 59.15 | 36.39