## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme |  |  | BILL/00211/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.97 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | New 3 phase connection at Phulberia W/S Scheme (near school) |  |  | BILL/00951/2024-2025 | BP-2024-25-229 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.44 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Sinking of 1 No. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas in connection with Augmentation of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000792/2022-2023 | 677/BQA | 28/03/2023 | 26/06/2023 | PARTHA PRATIM CHHATAIT | 92.98 | 48.49 | 52.15 | 81
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000779/2023-2024 | 2294/BMD | 26/12/2023 | 18/06/2025 | QUAZI NOZRUL ISLAM | 118.75 | 0 | 0 | 50
6 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 250 Cum., staging height 20 Mtr.) including by pass arrangement, construction of panel room, construction of boundary wall (Intake and OHR site), repairing of CWR, pump house and guard room with other allied works for Augmentation of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/001769/2024-2025 | 492/BQA | 25/02/2025 | 01/01/2026 | TARINI CHARAN UPADHYAY | 33.69 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of piped water supply scheme at Sarenga block, Phulberia , Gargaria water supply scheme under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000416/2025-2026 | 2023/BMD | 12/09/2025 | 11/12/2025 | M/S P.P ELECTRICALS | 57.8 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Phulberia piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Sarenga , Dist Bankura | Driller-in-Charge | Junior Engineer | ORD/000275/2024-2025 | 780/BMD | 20/08/2024 | 18/12/2025 | INDRAJIT MITRA | 16.02 | 0 | 0 | 80
9 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/17707 | Augmentation | Sinking of 1 No. 300 mm X 200 mm X 240 m deep Tubewell by Rig boring method, Laying of HDPE pipeline, Construction of Pump House, Construction of Boundary wall at Tubewell site and Sinking of 1 No. 200 mm dia x 5.5 mtr. depth horizontal river bed tube well using MS "T " and Laying, Fitting & fixing 100 mm M.S. delivery main connecting line from river bed tube well to CWR in connection with Augmentation of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000065/2024-2025 | 1520/BQA | 19/06/2024 | 02/01/2026 | TARINI CHARAN UPADHYAY | 68.26 | 0 | 0 | 30
Total | [13 empty] | 394.4 | 48.49 | 12.29