## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-A) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer |  | ORD/000545/2023-2024 | 1981/BMD | 28/08/2023 | 26/12/2023 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 34.93 | 22.84 | 65.37 | 66
2 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.11 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone - A) under Onda Block (BRGF Phase - I Project). | Assistant Engineer | Junior Engineer | ORD/000289/2023-2024 | 1910/BQA | 13/07/2023 | 08/04/2024 | JAI BHARAT COMMERCIAL CORPORATION | 153.6 | 153.59 | 99.99 | 85
4 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.11 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Construction of Boundary wall, Low Lift Pump house, Sinking of Tube well of Proposed Ground Water Based Nakaijuri PIped Water Supply Scheme & Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 812/BQA | 03/04/2025 | 01/01/2026 | GOUTAM GHOSH | 36.72 | 0 | 0 | 10
6 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Construction of Boundary wall at Tail end TW Site at Birsinghapur village in connection with Jal Jeevan Mission (JJM) for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Total Length:- 42 mtr.) | Assistant Engineer | Junior Engineer | ORD/000389/2025-2026 | 807/BSD | 01/09/2025 | 16/10/2025 | SUMAN DIHA | 4.76 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Soft stater Panel MCC Panel and other electromechanical acessories for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Estimator | ORD/000325/2024-2025 | 866/BMD | 29/08/2024 | 26/04/2025 | M.S. ENTERPRISE | 59.58 | 0 | 0 | 100
8 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Sinking of 1 (one) nos Tube well & Repairing and Renovation of RCC Elevated Over Head Reservoir under Augmentation of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2024-2025 | 2349/BQA | 09/09/2024 | 01/04/2026 | GOUTAM GHOSH | 27.12 | 0 | 0 | 100
Total | [13 empty] | 318.92 | 176.42 | 55.32