## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-A) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer |  | ORD/000545/2023-2024 | 1981/BMD | 28/08/2023 | 26/12/2023 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 34.93 | 0 | 0 | 66
2 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.11 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone - A) under Onda Block (BRGF Phase - I Project). | Assistant Engineer | Junior Engineer | ORD/000289/2023-2024 | 1910/BQA | 13/07/2023 | 08/04/2024 | JAI BHARAT COMMERCIAL CORPORATION | 153.6 | 0 | 0 | 85
4 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.11 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Sinking of 1 (one) nos Tube well & Repairing and Renovation of RCC Elevated Over Head Reservoir under Augmentation of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2024-2025 | 2349/BQA | 09/09/2024 | 01/01/2026 | GOUTAM GHOSH | 27.12 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Construction of Boundary wall, Low Lift Pump house, Sinking of Tube well of Proposed Ground Water Based Nakaijuri PIped Water Supply Scheme & Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 812/BQA | 03/04/2025 | 01/01/2026 | GOUTAM GHOSH | 36.72 | 0 | 0 | 10
7 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17708 | Augmentation | Construction of Boundary wall at Tail end TW Site at Birsinghapur village in connection with Jal Jeevan Mission (JJM) for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Total Length:- 42 mtr.) | Assistant Engineer | Junior Engineer | ORD/000389/2025-2026 | 807/BSD | 01/09/2025 | 16/10/2025 | SUMAN DIHA | 4.76 | 0 | 0 | 0
Total | [13 empty] | 259.34 | 0 | 0