## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000238/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.39 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-C) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000547/2023-2024 | 1983/BMD | 28/08/2023 | 15/12/2025 | KASHINATH DEY | 31.55 | 0 | 0 | 75
4 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000500/2023-2024 | 2350/BQA | 14/08/2023 | 01/04/2026 | ASHIS KUMAR SAMANTA | 278.43 | 0 | 0 | 72
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Additional Tubewell for Augmentation works for Aguribandh Punisole (Zone C) Water Supply Scheme in the Block Onda under Bankura Mechanical Division, PHE Dte | Assistant Engineer | Estimator | ORD/000874/2024-2025 | 2036/BMD | 07/03/2025 | 05/07/2025 | SWAPAN ENTERPRISE | 17.36 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Ceration of Balance FHTC with pipe line, Construction of 02 (Two) nos Pump House cum chlorine room (5.40 M X 3.6M) & Toilet with sanitary water supply arrangement including plinth protection, Ramp etc at Tail end TW-1 Site at Hirapur village & TW-2 Site at Kamla village and Construction of Boundary wall at Tail end TW- 1 Site at Hirapur village & TW- 2 Site in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Water Supply Scheme (BRGF Ph- I) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000073/2025-2026 | 1012/BQA | 25/04/2025 | 24/06/2025 | M/S SUPRIYA CHATTERJEE | 73.8 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Laying of UPVC Pipeline from Sahebganj more to Benajira village of damaged existing UPVC pipe line due to PWD Road Widening work for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2025-2026 | 1014/BQA | 25/04/2025 | 01/04/2026 | ASHIS KUMAR SAMANTA | 18.7 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17710 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-C) under Onda Block (BRGF Ph-I) at CWR site Nischintapur under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Estimator,Junior Engineer | ORD/000136/2024-2025 | 442/BMD | 27/06/2024 | 20/10/2025 | M.S. ENTERPRISE | 60.77 | 0 | 0 | 100
Total | [13 empty] | 487.4 | 0 | 0