## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17711 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-IIA (Baragari) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2022-2023 | 558/BQA | 17/03/2023 | 15/07/2023 | BIJOY KOLEY | 52.59 | 0 | 0 | 90
2 | BANKURA |  | Bankura Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17711 | Augmentation | Laying HDPE pipeline from Bantila More to Pithabaid village to increase pressure in Pithabaid (222) Mouza under Zone-IIA (Baragari) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 1108/BQA | 11/05/2023 | 25/06/2023 | SOUPTIK CHANDRA | 8.29 | 0 | 0 | 100
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17711 | Augmentation | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) |  |  | BILL/00210/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17711 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.91 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17711 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter Motorized Sulice valve with related allied works at Baragari (Zone-G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000023/2025-2026 | 234/BMD | 14/05/2025 | 12/08/2025 | JAL PRAVAHIKA PVT LTD | 28.18 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17711 | Augmentation | Laying HDPE pipeline from Baragari OHR to Mashra Village, Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) and Construction of Platform with all allied works in connection with Augmentation of Baragari Zone-IIA Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001575/2024-2025 | 335/BQA | 29/01/2025 | 15/03/2025 | D. S. ENTERPRISE | 13.27 | 0 | 0 | 0
Total | [13 empty] | 105.24 | 0 | 0