## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Augumentation of Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-B)under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000306/2023-2024 | 1954/BQA | 18/07/2023 | 01/06/2025 | SABIR ALI KHAN | 144.14 | 92.07 | 63.87 | 45
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-B) (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000554/2023-2024 | 1990/BMD | 28/08/2023 | 26/12/2023 | DIPALI CONSTRUCTION | 47.88 | 28.5 | 59.52 | 76
3 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.09 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electro-mechanical accessories for Augmentation works at CWPH at Gamidya under Nikunjapur Zone B water supply scheme (BRGF Ph I) Block Onda under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001078/2023-2024 | 3057/BMD | 12/03/2024 | 05/07/2025 | TAPAN KUMAR SARKAR | 38.32 | 8.95 | 23.35 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M Bg-. 213-29 /31) in between Rly. Station Ramsagar(RSG) & Onda Gram (ODM) Rly. station, P.S. Onda,by Jack Pushing method with 350 mm (OD) Spirally welded MS Casing Pipe with 200 mm dia. MS carrier pipe under Rejuvenation of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001137/2024-2025 | 2976/BQA | 26/11/2024 | 24/02/2025 | SIBSANKAR CHOWDHURY | 54.4 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000236/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.09 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17712 | Augmentation | Total payable load enhancement charges at Tetulmuri of Nikunjapur Zone-B ws scheme under BMD PHED. |  |  | BILL/00291/2024-2025 | 1 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.55 | 0 | 0 | 0
Total | [13 empty] | 289.47 | 129.52 | 44.74