## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 01) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000327/2023-2024 | 196/KSD | 13/07/2023 | 20/07/2023 | S. B. CONSTRUCTION | 0.97 | 0 | 0 | 95
2 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 02) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000328/2023-2024 | 197/KSD | 13/07/2023 | 20/07/2023 | S. B. CONSTRUCTION | 0.97 | 0 | 0 | 95
3 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 03) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000329/2023-2024 | 198/KSD | 13/07/2023 | 20/07/2023 | S. B. CONSTRUCTION | 0.97 | 0 | 0 | 90
4 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 04) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000330/2023-2024 | 199/KSD | 13/07/2023 | 20/07/2023 | S. B. CONSTRUCTION | 0.95 | 0 | 0 | 95
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. |  |  | BILL/00209/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Voltage Stabilizer and submersible pumping machineries with other allied works for Augmentation of Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000513/2024-2025 | 573/BMD | 23/07/2024 | 20/11/2024 | TAPAN KUMAR SARKAR | 25.19 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase-I) at tubewell No I Pump House No I under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001032/2023-2024 | 2964/BMD | 29/02/2024 | 27/08/2024 | INDRAJIT MITRA | 12.8 | 0 | 0 | 50
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No III Pump House No III under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001038/2023-2024 | 2970/BMD | 29/02/2024 | 27/08/2024 | M/S DAS & SARKAR ENTERPRISE | 12.76 | 0 | 0 | 50
9 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Laying of HDPE pipeline, Sinking of 3 Nos. 300 mm X 200 mm X 250 Metre deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000063/2024-2025 | 1484/BQA | 18/06/2024 | 16/09/2024 | SIBSANKAR CHOWDHURY | 96.77 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Relaying of distribution main by HDPE pipe along with allied works for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000825/2023-2024 | 2944/BQA | 30/10/2023 | 29/11/2023 | RAHIBUDDIN MANDAL | 11.74 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000834/2023-2024 | 2960/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.37 | 0 | 0 | 96
12 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Relaying of distribution main by HDPE pipe along with allied works for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000824/2023-2024 | 2943/BQA | 30/10/2023 | 27/02/2024 | M/S SUPRIYA CHATTERJEE | 11.74 | 0 | 0 | 100
13 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Additional work for Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Belatikri Zone-A water supply scheme(BRGF Ph-I) under Jal Jeevan Mission Progremme under Bankura Mechanical Division PHE Dte, Dist.-Bankura. | Driller-in-Charge | Junior Engineer | ORD/000011/2024-2025 | 519/BMSD(D) | 11/06/2024 | 02/07/2024 | M.S. ENTERPRISE | 2.8 | 0 | 0 | 100
14 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.96 | 0 | 0 | 0
15 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | New service connection for Belatikri Zone-A , Jl -39, Plot-233 |  |  | BILL/01153/2024-2025 | BP-2024-25-279 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0 | 0
16 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | New3 Phase Service Connection for Belatikri |  |  | BILL/00699/2024-2025 | BP-2024-25-162 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
17 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | New service connection for Belatikri Zone-A JL-30, Plot-104 |  |  | BILL/01151/2024-2025 | BP-2024-25-278 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0 | 0
18 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | New service connection for Belatikri water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00385/2024-2025 | BP-2024-25-83 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2023-2024 | 2039/BQA | 24/07/2023 | 19/04/2024 | UNIVERSAL CONSTRUCTION | 154.39 | 0 | 0 | 30
20 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No II Pump House No II under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001035/2023-2024 | 2967/BMD | 29/02/2024 | 10/02/2026 | PRADIP KUMAR DHABAL | 12.8 | 0 | 0 | 65
21 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001976/2024-2025 | 670/BQA | 12/03/2025 | 10/06/2025 | SAIKAT CHOWDHURY | 18.11 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Construction of 3 (Three) Nos. Pump House and Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2025-2026 | 832/BQA | 07/04/2025 | 08/10/2025 | TAPAS KUMAR HAZRA | 58.06 | 0 | 0 | 0
23 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000569/2023-2024 | 2026/BMD | 01/09/2023 | 28/02/2026 | M.S. ENTERPRISE | 96.39 | 0 | 0 | 70
Total | [13 empty] | 541.84 | 0 | 0