## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Dhemushunya (Zone-IV) and its adjoining Mouzas under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000752/2023-2024 | 2783/BQA | 09/10/2023 | 01/01/2026 | EARTH MOVING (INDIA) | 155.4 | 43.18 | 27.79 | 41
2 | BANKURA |  | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000837/2023-2024 | 2963/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 1.49 | 1.48 | 99.5 | 99
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/00208/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Dhemusunya under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000287/2024-2025 | 2096/BQA | 05/08/2024 | 30/09/2025 | ASHOK KUMAR DEY | 48.19 | 0 | 0 | 20
5 | BANKURA |  | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Dhemusunya under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000285/2024-2025 | 2097/BQA | 05/08/2024 | 01/04/2025 | M/S SUPRIYA CHATTERJEE | 48.19 | 0.57 | 1.18 | 70
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Acceptance cum Formal work order for the work of Miscellaneous work for Gaseous Chlorination System at Head work site for Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division PHE Dte, | Driller-in-Charge | Junior Engineer | ORD/001096/2023-2024 | 3071/BMD | 12/03/2024 | 02/11/2025 | EASTERN INDIA SALES & SERVICE | 14.32 | 13.41 | 93.67 | 80
7 | BANKURA |  | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.77 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room, Boundary Wall and Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with all allied works of Augmentation works for Dhemusunya Zone-IV Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2025-2026 | 1290/BQA | 17/06/2025 | 18/12/2025 | UTTAM KUMAR SINHAMAHAPATRA | 37.99 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17714 | Augmentation | Acceptance cum Formal work order for the work of Augmentation work for Dhemusunia (Zone IV) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000879/2024-2025 | 2039/BMD | 07/03/2025 | 05/07/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 95.37 | 0 | 0 | 10
Total | [13 empty] | 404.73 | 58.64 | 14.49