## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme |  |  | BILL/00207/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.85 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Augmentation works for Chiltore and its Adjoining mouzas water supply scheme under Jal Jeevan Mission programe under Bankura Mechanical Division PHE Dte, Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000717/2023-2024 | 2174/BMD | 30/10/2023 | 26/02/2026 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 62.99 | 54.24 | 86.11 | 80
4 | BANKURA |  | Bankura Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 200 Cum., staging height 20 Mtr.), CWR, Pump House cum Chlorine Room and Construction of Boundary Wall and Guard Room with all allied works of Augmentation of Chiltore water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001979/2024-2025 | 672/BQA | 12/03/2025 | 12/12/2025 | SUBHADIP KOLE | 49.61 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries and allied works for Augmentation of Chiltore water supply scheme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000019/2025-2026 | 154/BMD | 30/04/2025 | 29/07/2025 | DEBJYOTI BASU | 10.26 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Laying additional HDPE pipeline, supply of sluice valve and construction of valve chamber with all allied works under Augmentation works for Chiltore and Its Adjoining mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2025-2026 | 1308/BQA | 17/06/2025 | 17/12/2025 | SUBHAJIT BANERJEE | 20.49 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Acceptance cum Formal work order for the work of Construction of one no RBTW with providing and installation of Neutralization System , installation of 1 no Submersible Pump Motor set other work at Chiltore water supply scheme under Sarenga Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000193/2025-2026 | 638/BMD | 11/07/2025 | 09/10/2025 | GOENKA ENTERPRISE | 33.03 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Construction & commissioning of FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Chiltore and its adjoining Mouzas Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1924/BQA | 13/07/2023 | 08/04/2024 | SUBHADIP KOLEY | 104.26 | 91.65 | 87.9 | 100
9 | BANKURA |  | Bankura Mechanical | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Acceptance cum Formal work order for the work of Supply and installation of submersible pumping machinery and Voltage Stabilizer with allied items for Augmentation for Chiltore water supply scheme under Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000173/2024-2025 | 515/BMD | 09/07/2024 | 21/12/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 15.77 | 0 | 0 | 60
10 | BANKURA |  | Bankura Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | SM/17725 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works for Augmentation works for Chiltore and Its Adjoining mouzas Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000193/2025-2026 | 1328/BQA | 17/06/2025 | 01/11/2025 | UTTAM KUMAR SINHAMAHAPATRA | 21.78 | 0 | 0 | 90
Total | [13 empty] | 321.04 | 145.89 | 45.44