## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Work Order for Extension of distribution pipeline by UPVC pipe (6Kg/Sq. Cm. Water Pressure, class III) along with allied works at Rakhapara village of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000455/2023-2024 | 263/KSD | 24/08/2023 | 08/09/2023 | S. B. CONSTRUCTION | 0.96 | 0.96 | 99.75 | 95
2 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2022-2023 | 561/BQA | 17/03/2023 | 01/05/2023 | MAHARAJA CONSTRUCTION CO. | 44.9 | 44.68 | 99.52 | 40
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) |  |  | BILL/00205/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.34 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Laying of distribution pipeline, providing FHTC (Functional House Hold Tap Connection), Construction of platform, valve chamber with all allied works of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part:-B) | Assistant Engineer |  | ORD/002026/2024-2025 | 689/BQA | 12/03/2025 | 11/05/2025 | SUMITA UPADHYAY | 18.15 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Bhuakhana under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000045/2025-2026 | 249/BMD | 14/05/2025 | 12/08/2025 | ORIENTAL ENGINEERING CO. | 28.14 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Laying of distribution pipeline, providing FHTC (Functional House Hold Tap Connection), Construction of platform, valve chamber with all allied works of Zone-A (Bhuakana) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part:-A) | Assistant Engineer |  | ORD/001964/2024-2025 | 663/BQA | 12/03/2025 | 11/05/2025 | GON ASSOCIATES | 18.15 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17730 | Augmentation | Laying HDPE pipeline from Rajadali village to Purnadihi village and from Hirbandh OHR site (Soul Ponamara) to Bijardihi village, in connection with Augmentation of Bhuakana (Zone-A) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001555/2024-2025 | 301/BQA | 28/01/2025 | 16/07/2025 | GON ASSOCIATES | 10.62 | 0 | 0 | 90
Total | [13 empty] | 124.25 | 45.64 | 36.73