## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-B (Tilaboni) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000609/2022-2023 | 566/BQA | 17/03/2023 | 01/05/2023 | M/S SUPRIYA CHATTERJEE | 61.85 | 61.4 | 99.28 | 100
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) |  |  | BILL/00204/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Laying HDPE pipeline, Construction and Commissioning of FHTC (Functional House Hold Tap Connection), Construction of platform with all allied works of Zone-B (Tilabani) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 401/BQA | 07/02/2024 | 02/03/2026 | M/S PARAMESWAR CHOWDHURY | 54.4 | 36.43 | 66.97 | 87
4 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.59 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 738/BQA | 01/03/2024 | 01/03/2024 | Resource Division | 25.98 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17731 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Tilaboni (Zone B ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000058/2025-2026 | 254/BMD | 14/05/2025 | 12/08/2025 | S.P. CONSTRUCTION | 28.43 | 0 | 0 | 0
Total | [13 empty] | 174.25 | 97.84 | 56.15