## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Vishnupur | Bankura Division | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 15.8 | 0 | 0 | 0
2 | BANKURA | Vishnupur | Bankura Mechanical | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | Jamuna Band Pipe Water Supply Scheme |  |  | BILL/00173/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
3 | BANKURA | Vishnupur | Bankura Division | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | Preparation of Detailed Project Report for Proposed ground water based JAMUNA BAND pipe water supply scheme, under Bankura Division Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001210/2023-2024 | 484/BQA | 09/02/2024 | 08/07/2024 | ROY CHOWDHURY ASSOCIATES | 3.56 | 3.56 | 100 | 91
4 | BANKURA | Vishnupur | Bankura Mechanical | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | Submission of Quotation for new service connection at Jamunabundh TW-I W/S scheme under BMD.PHE Dte. SM/18037 |  |  | BILL/00497/2024-2025 | BP-2023-24- | 28/11/2024 | 28/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0 | 0
5 | BANKURA | Vishnupur | Bankura Division | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR JAMUNABANDH PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000374/2023-2024 | 2036/BQA | 24/07/2023 | 01/11/2025 | DEBAKI RANJAN SARKAR | 457.16 | 205.77 | 45.01 | 90
6 | BANKURA | Vishnupur | Bankura Mechanical | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Jamuna Bandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000442/2023-2024 | 1771/BMD | 01/08/2023 | 23/06/2025 | M/S BIPUL BANERJEE | 36.9 | 20.14 | 54.6 | 65
7 | BANKURA | Vishnupur | Bankura Mechanical | Jamuna Band Pipe Water Supply Scheme | SM/18037 | New | Quotation for new service connection at Jamunabundh T/W-II.SM/18037 |  |  | BILL/01354/2024-2025 | BP-2024-25-330 | 13/01/2025 | 13/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.18 | 0 | 0 | 0
Total | [13 empty] | 526.29 | 229.48 | 43.6