## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sarenga | Bankura Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 0.98 | 0 | 0 | 0
2 | BANKURA | Sarenga | Bankura Mechanical | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA |  |  | BILL/00203/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
3 | BANKURA | Sarenga | Bankura Mechanical | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Bansi piped water supply scheme Block Sarenga under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000464/2023-2024 | 1806/BMD | 03/08/2023 | 01/12/2023 | M/S BIPUL BANERJEE | 35.21 | 16.42 | 46.65 | 35
4 | BANKURA | Sarenga | Bankura Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | Preparation of Detailed Project Report for Proposed Ground Water Based Bansi Pipe Water Supply Scheme under Bankura Division, Block : Sarenga, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001078/2023-2024 | 3540/BQA | 29/12/2023 | 28/01/2024 | LEMNISCATE | 2.62 | 2.55 | 96.97 | 90
5 | BANKURA | Sarenga | Bankura Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.92 | 0 | 0 | 0
6 | BANKURA | Sarenga | Bankura Mechanical | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | New 3 phase connection for Banshi water Supply Scheme |  |  | BILL/00949/2024-2025 | BP-2024-25-227 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.87 | 0 | 0 | 0
7 | BANKURA | Sarenga | Bankura Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | Sinking of 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of 100 Cum. Clear Water Reservoir, Pump House, Boundary Wall, Distribution pipeline with ancillary works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Ground Water Based Bansi Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000528/2023-2024 | 2362/BQA | 14/08/2023 | 02/01/2026 | SOUHARDYA BUSINESSLINE | 125.04 | 60.54 | 48.42 | 80
8 | BANKURA | Sarenga | Bankura Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | SM/18038 | New | Sinking of 300 mm X 200 mm X 150 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Pump house & Boundary wall at tubewell Site for Ground Water Based Bansi Piped Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000184/2025-2026 | 1322/BQA | 17/06/2025 | 01/11/2025 | M/S. AMAL KUMAR SARKAR | 27.39 | 0 | 0 | 0
Total | [13 empty] | 200.03 | 79.51 | 39.75