## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 91.73 | 0 | 0 | 0
2 | BANKURA | Khatra | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Khayerbani piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000566/2023-2024 | 2033/BMD | 01/09/2023 | 20/04/2025 | RAJIB COMPANY | 45.28 | 21.8 | 48.14 | 48
3 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 4.95 | 0 | 0 | 0
4 | BANKURA | Khatra | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA |  |  | BILL/00201/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
5 | BANKURA | Khatra | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA |  |  | BILL/01662/2023-2024 | BP-2023-24-177 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | 0
6 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | SConstruction of 2 Nos. 100 Cum Clear Water Reservoir for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000690/2023-2024 | 2636/BQA | 21/09/2023 | 20/12/2023 | SUBHADIP KOLE | 47.49 | 16.71 | 35.18 | 30
7 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000762/2023-2024 | 2866/BQA | 11/10/2023 | 02/11/2025 | TAPAS PAL | 38.91 | 0 | 0 | 0
8 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000764/2023-2024 | 2867/BQA | 11/10/2023 | 01/04/2026 | M/S SUPRIYA CHATTERJEE | 38.91 | 0 | 0 | 38
9 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Laying Rising Main of Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000689/2023-2024 | 2635/BQA | 21/09/2023 | 24/03/2026 | M/S. AMAL KUMAR SARKAR | 12.56 | 0 | 0 | 50
10 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000688/2023-2024 | 2634/BQA | 21/09/2023 | 02/01/2025 | SUBHENDU SEKHAR GORAI | 21.16 | 16.11 | 76.14 | 70
11 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Construction of 2 Nos. Pump House with ancillary works for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000756/2023-2024 | 2863/BQA | 11/10/2023 | 02/02/2025 | SUBHAJIT BANERJEE | 15.32 | 12.7 | 82.84 | 40
12 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Construction Boundary wall at CWR site of Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000865/2023-2024 | 3018/BQA | 03/11/2023 | 28/09/2025 | SWAPAN KUMAR PATRA | 12.42 | 8.66 | 69.7 | 90
Total | [13 empty] | 333.93 | 75.97 | 22.75