## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 26.04 | 0 | 0 | 0
2 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.99 | 0 | 0 | 0
3 | BANKURA | Barjora | Bankura Mechanical | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. |  |  | BILL/00198/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
4 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Rail bhoomi crossing seva |  |  | BILL/00934/2023-2024 | FHTC/08 | 31/08/2023 | 31/08/2023 | SOUTH EASTERN RAILWAY | 0.53 | 0 | 0 | 0
5 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS DHABANI PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- BARJORA, DISTRICT -BANKURA . NAME OF MUZA - KANCHCHHALA, SAMANTAMARA & DHABANI UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2023-2024 | 2275/BQA | 01/08/2023 | 01/12/2025 | PRADIP RAJAK | 349.81 | 165.08 | 47.19 | 62
6 | BANKURA | Barjora | Bankura Mechanical | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Proposed surface water based Dhabani under Water Supply Scheme Block- Barjora under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1769/BMD | 01/08/2023 | 30/09/2023 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 45.35 | 26.22 | 57.83 | 31
7 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Soil Investigation work for construction of OHR (100 CUM CAPACITY) under Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000895/2023-2024 | 3046/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.57 | 0.55 | 95.71 | 100
8 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Material Requisition To Resource Division |  |  | RTOR000233/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.99 | 0 | 0 | 0
9 | BANKURA | Barjora | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | Route Survey Preparation of DPR for piped water supply scheme for uncover mouzas of Kanchchala (JL No- 126), Samantamara (127) & Dhabani (JL No- 128) Block- Barjora under Jal Jeevan Misson (JJM) of Bankura Sadar Sub - Division under Bankura Division, PHE Dte . | Assistant Engineer | Junior Engineer | ORD/000852/2023-2024 | 2978/BQA | 31/10/2023 | 30/11/2023 | LEMNISCATE | 2.67 | 0 | 0 | 100
10 | BANKURA | Barjora | Bankura Mechanical | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | SM/18041 | New | New Service connection charge at Dhabani water supply scheme (CWR, OHR site), Barjora block under BMD, PHE Dte. (SM/1804) |  |  | BILL/01336/2024-2025 | BP-2024-25-329 | 29/01/2025 | 29/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.3 | 0 | 0 | 0
Total | [13 empty] | 440.27 | 191.86 | 43.58