## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 51.54 | 0 | 0 | 0
2 | BANKURA | Khatra | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA |  |  | BILL/00200/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
3 | BANKURA | Khatra | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Pirra Bakra piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000571/2023-2024 | 2035/BMD | 01/09/2023 | 30/12/2023 | M/S BIPUL BANERJEE | 35.44 | 0 | 0 | 65
4 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
5 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Preparation of Detailed Project Report for Proposed Sub Surface Water Based Pirra Bakra Pipe Water Supply Scheme under Bankura Division, Block : Khatra, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001079/2023-2024 | 3542/BQA | 29/12/2023 | 28/01/2024 | LEMNISCATE | 2.76 | 0 | 0 | 90
6 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 6.07 | 0 | 0 | 0
7 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of Clear Water Reservoir, Construction of Pump House, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pirrabakra pipe water supply scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000502/2023-2024 | 2352/BQA | 14/08/2023 | 15/03/2026 | S B ASSOCIATES | 223.33 | 0 | 0 | 80
8 | BANKURA | Khatra | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Balance work of Rising Main for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme and Proposed Sub-Surface Water Based Pirra Bakra Pipe Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000196/2025-2026 | 1410/BQA | 26/06/2025 | 01/12/2025 | PRADIP PATRA | 10.35 | 0 | 0 | 0
9 | BANKURA | Khatra | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18042 | New | Acceptance cum Formal work order for the work of Providing, installation of Low lift Pumping machineries with other electro mechanical accessories for 2nd no tubewell for proposed ground water based Pirra Bankra piped water supply scheme Block Khatra under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | Driller-in-Charge | Junior Engineer | ORD/000881/2024-2025 | 2041/BMD | 07/03/2025 | 02/11/2025 | M/S BIPUL BANERJEE | 9.91 | 0 | 0 | 60
Total | [13 empty] | 346.56 | 0 | 0