## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works, Construction of Clear Water Reservoir, Pump House, Boundary Wall with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub-surface Water Based Handulia Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2023-2024 | 2088/BQA | 27/07/2023 | 02/01/2026 | SANJOY PATRA | 250.83 | 79.16 | 31.56 | 82
2 | BANKURA | Simlapal | Bankura Mechanical | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Handulia piped water supply scheme Block Simlapal under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000564/2023-2024 | 2031/BMD | 01/09/2023 | 15/12/2025 | M/S SOMA ENTERPRISES | 48.85 | 35.67 | 73.01 | 30
3 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
4 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Preparation of Detailed Project Report for Proposed sub-surface Water Based Handulia Piped Water Supply Scheme under Bankura Division, Block-Simlapal, District-Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001081/2023-2024 | 3544/BQA | 29/12/2023 | 28/01/2024 | LEMNISCATE | 2.81 | 2.78 | 98.98 | 90
5 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 23.61 | 0 | 0 | 0
6 | BANKURA | Simlapal | Bankura Mechanical | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. |  |  | BILL/00199/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
7 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.47 | 0 | 0 | 0
8 | BANKURA | Simlapal | Bankura Mechanical | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | New service connection of Handulia PWSS ,Mouza-Ramchandrapur, G.p.- Parsala JL No.-5 Plot no.-8 under BMSD(D) PHE Dte. |  |  | BILL/00001/2024-2025 | BP-2024-25-96 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0 | 0
9 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Work Order for Installation of scheme information board for 5 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17440] and 1 no. site of Proposed sub-surface Water Based Handulia Piped Water Supply Scheme (SM/18044) within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001925/2024-2025 | 169\KSD | 07/03/2025 | 17/03/2025 | PRADYUMNA KOLEY | 0.9 | 0 | 0 | 90
10 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Repair and Maintenance work of the Road from Bagdoba to Ramchandrapur Via Goalbathan under Simlapal Block in the District of Bankura,Vide Package No- Road Length-2.2 Km. (Proposed sub-surface water based Handulia Pipe water supply scheme.) |  |  | BILL/01440/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0 | 0
11 | BANKURA | Simlapal | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | SM/18044 | New | Repair and Maintenance work of the Road from L053-Ramchandrapur to Bhelaidiha under Simlapal Block in the District of Bankura ,Vide Package No-WB-03-406, Road Length-3.864 Km.( proposed sub-surface water based Handulia pipe water supply scheme) |  |  | BILL/01438/2024-2025 | BP/569/2024-25 | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.79 | 0 | 0 | 0
Total | [13 empty] | 343.8 | 117.6 | 34.21