## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | Augmentation of Sashpur Zone-A Water Supply Scheme |  |  | BILL/00174/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sashpur (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000381/2023-2024 | 1705/BMD | 28/07/2023 | 27/09/2024 | A.G.ENTERPRISE | 75.74 | 35.75 | 47.2 | 60
3 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | Load enhancement charges for SASHPUR ZONE A water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00437/2024-2025 | BP-2024-25-111 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | Augmentation of Sashpur Zone-A Water Supply Scheme |  |  | BILL/01623/2023-2024 | BP-2023-24-159 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF SASHPUR ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1922/BQA | 13/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 200.83 | 91.11 | 45.37 | 80
6 | BANKURA |  | Bankura Division | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Sashpur (Zone-A) Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001398/2024-2025 | 23/BQA | 02/01/2025 | 02/04/2025 | MANI SANKAR MUKHERJEE | 12.96 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Sashpur Zone-A Water Supply Scheme | SM/18114 | Augmentation | Instalation of scheme information board for 2 nos. sites of Augmentation of Sashpur Zone-A Water Supply Scheme (SM/18114 ), 3 nos. sites of Augmentation of Sashpur Zone-B Water Supply Scheme (SM/17421) & 1 no. site of Augmentation of Somsar (BRGF) Water Supply Scheme (SM/17579) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001821/2024-2025 | 542/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.9 | 0 | 0 | 0
Total | [13 empty] | 295.78 | 126.86 | 42.89