## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/18119 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.07 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/18119 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chaknakaijuri & its adjoining Mouzas water supply scheme under Onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000540/2023-2024 | 1976/BMD | 28/08/2023 | 01/05/2025 | INDRAJIT MITRA | 56.67 | 36.52 | 64.44 | 70
3 | BANKURA |  | Bankura Division | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/18119 | Augmentation | Augumentation of Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000401/2023-2024 | 2086/BQA | 27/07/2023 | 17/01/2025 | DIVINE | 175.17 | 110.56 | 63.11 | 80
4 | BANKURA |  | Bankura Division | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/18119 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000230/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.07 | 0 | 0 | 0
Total | [13 empty] | 235.98 | 147.08 | 62.33