## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18231 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-CE (Ashatora) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000603/2022-2023 | 556/BQA | 17/03/2023 | 15/06/2023 | LABIR MIRSHAD KHAN | 19.63 | 19.32 | 98.42 | 90
2 | BANKURA |  | Bankura Division | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/18231 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.91 | 0 | 0 | 0
Total | [13 empty] | 21.54 | 19.32 | 89.7