## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Danna Piped Water Supply Scheme. | SM/18302 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 245.78 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000125/2024-2025 | 1073/BMSD | 05/07/2024 | 03/09/2024 | KASHINATH DEY | 4.38 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at P/H of adjoining mouza of Danna piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000126/2024-2025 | 1075/BMSD | 05/07/2024 | 03/09/2024 | KINGKINI TRADERS | 4.39 | 4.27 | 97.26 | 100
4 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danna Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 883/BMD | 04/05/2023 | 20/09/2025 | M/S NABIN GOPAL SENGUPTA | 68.09 | 29.42 | 43.21 | 55
5 | BANKURA | Patrasayer | Bankura Division | Danna Piped Water Supply Scheme. | SM/18302 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DANNA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000467/2023-2024 | 2322/BQA | 14/08/2023 | 01/06/2026 | DEBAKI RANJAN SARKAR | 683.53 | 146.17 | 21.38 | 65
6 | BANKURA | Patrasayer | Bankura Division | Danna Piped Water Supply Scheme. | SM/18302 | New | Sinking of 1 no Tubewell and Construction of Boundary wall for Augmentation of Patrasayer Water Supply Scheme & Danna Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001938/2024-2025 | 653/BQA | 11/03/2025 | 04/03/2026 | BROTIN UPADHYAY | 20.43 | 0 | 0 | 71
7 | BANKURA | Patrasayer | Bankura Mechanical | Danna Piped Water Supply Scheme. | SM/18302 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Danna Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000034/2025-2026 | 239/BMD | 14/05/2025 | 12/08/2025 | M/S NABIN GOPAL SENGUPTA | 12.46 | 0 | 0 | 0
Total | [13 empty] | 1039.07 | 179.86 | 17.31