## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Indus,Kotulpur | Bankura Division | Bagdoba Piped Water Supply Scheme | SM/18305 | New | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 167.01 | 0 | 0 | 0
2 | BANKURA | Indus,Kotulpur | Bankura Mechanical | Bagdoba Piped Water Supply Scheme | SM/18305 | New | Bagdoba Piped Water Supply Scheme |  |  | BILL/01547/2023-2024 | BP-2023-24-93 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.38 | 0 | 0 | 0
3 | BANKURA | Indus,Kotulpur | Bankura Mechanical | Bagdoba Piped Water Supply Scheme | SM/18305 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Bagdoba Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000169/2023-2024 | 881/BMD | 04/05/2023 | 18/04/2026 | TAPAN KUMAR SARKAR | 47.08 | 26.89 | 57.11 | 60
4 | BANKURA | Indus,Kotulpur | Bankura Division | Bagdoba Piped Water Supply Scheme | SM/18305 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BAGDOBA & KHUNDANGA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 2332/BQA | 14/08/2023 | 04/02/2025 | GOPAL CHANDRA CHOWDHURY | 1262.72 | 177.44 | 14.05 | 80
5 | BANKURA | Indus,Kotulpur | Bankura Division | Bagdoba Piped Water Supply Scheme | SM/18305 | New | Instalation of scheme information board for 2 nos. sites of Khundanga Piped Water Supply Scheme (SM/14482) , 2 nos. sites of Jibta Piped Water Supply Scheme (SM/15018) & 2 nos. sites of Bagdoba Piped Water Supply Scheme (SM/18305) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001875/2024-2025 | 553/VSD | 27/09/2024 | 12/10/2024 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 0 | 100
Total | [13 empty] | 1484.09 | 204.33 | 13.77